## Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Planning Stage | 1 | 1 | 1 | 4 | 100%
Create Gantt Chart | 1 | 1 | 1 | 1 | 100%
Concept Art | 3 | 1 | 3 | 2 | 100%
Come up with required tasks | 1 | 1 | 1 | 1 | 100%
Level Design Document | 2 | 3 | 2 | 4 | 0%
Setting | 2 | 1 | 2 | 1 | 100%
Theme | 2 | 1 | 2 | 1 | 100%
Focal Points | 2 | 1 | 2 | 2 | 100%
Locations | 3 | 1 | 3 | 2 | 100%
Level Features | 3 | 1 | 3 | 1 | 100%
Usability and Gameplay Reference and Research | 4 | 1 | 4 | 2 | 100%
Photo/Video Reference and Research | 4 | 1 | 4 | 1 | 100%
Lighting | 4 | 1 | 4 | 1 | 100%
Inspiration | 4 | 1 | 4 | 1 | 100%
Story | 3 | 1 | 3 | 2 | 100%
Controls | 2 | 1 | 2 | 1 | 100%
Enemies | 4 | 1 | 4 | 1 | 100%
Development | 4 | 5 | 4 | 4 | 50%
Block out level | 4 | 1 | 4 | 2 | 100%
Create static assets | 4 | 1 | 4 | 2 | 100%
Create player model | 5 | 1 | 5 | 1 | 100%
Create enemy models | 5 | 1 | 5 | 1 | 50%
Create enemy scripts | 6 | 1 | 6 | 2 | 33%
Create obsticles | 6 | 3 | 6 | 2 | 20%
Create scenery textures | 7 | 1 | 7 | 1 | 25%
Setup level lighting | 8 | 1 | 0 | 0 | 0%
Testing | 9 | 4 | 0 | 0 | 0%
In-house testing | 9 | 1 | 0 | 0 | 0%
Beta user testing | 10 | 1 | 0 | 0 | 0%
Alpha user testing | 11 | 1 | 0 | 0 | 0%
Formal evaluation | 12 | 1 | 0 | 0 | 0%